## WBS
WBS ID | Phase | Work Package / Task | Owner Role | Start Date | End Date | Duration (Days) | Dependency | Status
1.1 | Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | Rewrite content pipeline to human-sourced-first model (AI limited to draft-translation assist only) | Backend / Geospatial Engineer | 2026-09-07 | 2026-09-08 | 2 |  | Not Started
1.2 | Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | Draft outreach message to Kimberley Big Hole & Diamond Museum | Partnerships / Go-to-Market Lead | 2026-09-07 | 2026-09-08 | 2 |  | Not Started
1.3 | Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | Draft outreach message to Matjiesfontein heritage village | Partnerships / Go-to-Market Lead | 2026-09-08 | 2026-09-09 | 2 |  | Not Started
1.4 | Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | Verify real waypoint coordinates for all 8 stations against published station records | Backend / Geospatial Engineer | 2026-09-07 | 2026-09-08 | 2 |  | Not Started
1.5 | Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | Finalize WBS and consumer-phasing plan (this document) | Partnerships / Go-to-Market Lead | 2026-09-09 | 2026-09-10 | 2 |  | Not Started
2.1 | Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | Build integrated FastAPI journey-position service (route + geofence + content store) | Backend / Geospatial Engineer | 2026-09-10 | 2026-09-13 | 4 | 1.1 | Not Started
2.2 | Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | Build MapLibre animated route frontend (Explorer Mode skeleton) | Frontend / Map Animation Developer | 2026-09-11 | 2026-09-16 | 6 |  | Not Started
2.3 | Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | Wire frontend to integrated API — first true end-to-end lab demo | Frontend / Map Animation Developer | 2026-09-16 | 2026-09-18 | 3 | 2.1, 2.2 | Not Started
2.4 | Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | Write end-to-end integration test suite (not just unit tests) | Backend / Geospatial Engineer | 2026-09-13 | 2026-09-14 | 2 | 2.1 | Not Started
2.5 | Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | Human review pass on all seeded story content before it ships | UX & Cultural Content Lead | 2026-09-14 | 2026-09-16 | 3 |  | Not Started
3.1 | Phase 3: Consumer-Phasing Prep (18–24 Sep) | Recruit 10–15 friends/family for closed Phase 0 pilot | Partnerships / Go-to-Market Lead | 2026-09-18 | 2026-09-20 | 3 |  | Not Started
3.2 | Phase 3: Consumer-Phasing Prep (18–24 Sep) | Run closed pilot walkthrough sessions and collect feedback | UX & Cultural Content Lead | 2026-09-20 | 2026-09-22 | 3 | 3.1 | Not Started
3.3 | Phase 3: Consumer-Phasing Prep (18–24 Sep) | Incorporate pilot feedback into Explorer Mode UX | Frontend / Map Animation Developer | 2026-09-22 | 2026-09-24 | 3 | 3.2 | Not Started
3.4 | Phase 3: Consumer-Phasing Prep (18–24 Sep) | Prepare judge-facing pitch deck and live demo script | Partnerships / Go-to-Market Lead | 2026-09-19 | 2026-09-23 | 5 |  | Not Started
3.5 | Phase 3: Consumer-Phasing Prep (18–24 Sep) | Rehearse live demo end-to-end with full team | All | 2026-09-23 | 2026-09-24 | 2 | 3.4 | Not Started
4.1 | Phase 4: Hackathon Weekend (25–27 Sep, BCX HQs Centurion) | Day 1 — team sync and final build push | All | 2026-09-25 | 2026-09-25 | 1 |  | Not Started
4.2 | Phase 4: Hackathon Weekend (25–27 Sep, BCX HQs Centurion) | Day 2 — full run-through and judge Q&A preparation | All | 2026-09-26 | 2026-09-26 | 1 | 4.1 | Not Started
4.3 | Phase 4: Hackathon Weekend (25–27 Sep, BCX HQs Centurion) | Day 3 — final polish, submission, live pitch | All | 2026-09-27 | 2026-09-27 | 1 | 4.2 | Not Started
5.1 | Phase 5: Post-Hackathon Consumer Rollout (28 Sep onward) | Phase 0 — closed-pilot retro and fixes from hackathon feedback | Backend / Geospatial Engineer | 2026-09-28 | 2026-10-05 | 8 | 4.3 | Not Started
5.2 | Phase 5: Post-Hackathon Consumer Rollout (28 Sep onward) | Phase 1 — limited public pilot with one confirmed operator partner (Rovos Rail or Blue Train) | Partnerships / Go-to-Market Lead | 2026-10-06 | 2026-10-31 | 26 | 5.1 | Not Started
5.3 | Phase 5: Post-Hackathon Consumer Rollout (28 Sep onward) | Phase 2 — broader public Explorer Mode launch (no operator dependency) | All | 2026-11-01 | 2026-11-30 | 30 | 5.2 | Not Started

## Phase Summary
Phase | Total Tasks | Not Started | In Progress | Done | % Complete
Phase 1: Reality Alignment & Content Sourcing (7–10 Sep) | 5 | 5 | 0 | 0 | 0%
Phase 2: TRL 4 Lab Integration Build (10–18 Sep) | 5 | 5 | 0 | 0 | 0%
Phase 3: Consumer-Phasing Prep (18–24 Sep) | 5 | 5 | 0 | 0 | 0%
Phase 4: Hackathon Weekend (25–27 Sep, BCX HQs Centurion) | 3 | 3 | 0 | 0 | 0%
Phase 5: Post-Hackathon Consumer Rollout (28 Sep onward) | 3 | 3 | 0 | 0 | 0%
TOTAL | 21 | 21 | 0 | 0 | 0%